## Slide 1: Output O5 and O7
March 5-6
Alcala, Ljubljana, Warsaw

## Slide 2: Literacy units (O5)
Literacy units in transnational teams should be completed by March, 31st, 2020
Creating of teams and preliminary work on text selection (February)
Creating the units and the materials (March)
Bilinguis will be supervising the process of creating the units by making sure all the groups are moving forward and all group members are contributing
Collect the units of all groups by March, 31st, 2020
Each school partner has 35 days to complete the units (billable days)

## Slide 3: Literacy units
Plan a literacy unit based on a selected text that has been agreed by the team members
It can be a non-fiction or a fiction text
The unit should be written using the unit literacy grid
It should include all the phases including:
  The unit overview page;
  reception A, B and C;
  production A and B.
The time frame – minimum of 4 lessons

## Slide 4: Repository O7
The literacy units will be implemented April-June, 2020 (25 billable days for each school partner for implementing and creating the evidence)
The transnational teacher teams will have to decide which evidence should be included in the repository by June, 30th
All the materials should be sent to the university partners for additional evaluation before June, 30th
All the materials should be sent to the University of Warsaw by July, 7th, 2020
Group leaders will upload the materials by July-September, 20th, 2020
University of Warsaw will present the beta version of the Repository by September, 30th, 2020

## Slide 5: Repository
University of Warsaw will create the website - the structure will be ready by June-July, 2020
University of Warsaw will create accounts for each of the group leader to upload the materials (June, 2020)
Technical support for schools - help with videotaping, preparing the videos, sound, etc. (7 payable days for technical support)

## Slide 6: Collecting evidence from the units
Each international group of 3 teachers gathers the evidence on their shared unit, consisting of:
  Planning grid
  The text itself
  Student work
  Videos
  Tasks
  Worksheets
  Presentations
  Etc.

## Slide 7: The evidence: videos of literacy units
1. A: Reception (Phase 1 and Phase 2); B: Observing; C: Analyzing; D: Production (Guided and Free) (4 movies, one for each phase, ideally 5- max 10 min – short and meaningful)
2. Teacher commentary: pre-commentaries, justification of task and text selection, post-teaching reflections (shot as separate files) (2 movies) short commentaries for each phase (2-3 minutes, max of 5 min)
1 short video of student‘s reacting to the unit
Student production (can also be spoken, not only written)
All teachers at school record, the international group decides which videos to put into the repository.

## Slide 8: Repository technical information
Video materials (mp4, full HD (1920x1080 px)
Telephone camera or other camera’s,
Using the camera stand,
Shot in the landscape orientation)
Two cameras (best scenario)

## Slide 9
Ensure even lighting. It is important to have uniform lighting in a room to avoid harsh backlighting that makes the subject appear dark. If possible, situate point the camera away from a bright window or other light source.
Frame the shot. Make sure the camera is facing the subject of the video and that everything fits in the frame.
Steady the camera. Place the camera on a flat surface, prop it against a book or wall, or use a tripod or flexible stand to avoid a shaky, hand-held shot.

## Slide 10
Clean the lens. Fingerprints or smudges on the device’s lens will can ruin an otherwise perfect shot. Make sure to clean off the lens before hitting record.
Avoid background noise. Make sure the camera is away from any machine or object – such as a fan or air conditioning unit – that might add background noise.
Keep in mind the microphone. Regardless if the camera is using an external mic or a built-in one, make sure it is not blocked by a finger or muffled by a case.
Get close to the source. Place the camera as close as possible to the source of the audio to avoid any unwanted sounds, such as students whispering or papers shuffling. Since microphones are designed to pick up all noise, the closer the microphone is to the source, the better.
https://www.techlearning.com/tl-advisor-blog/7-tips-for-capturing-high-quality-video-of-classroom-teaching